## Sheet1
ToDo List
Story | Estimation(days) | Priority | Complete
As a user I want to see the Barber Shop Hours | 1 | Low | Yes
As a user I want to make an appointment | 7 | High | Yes
As a user I want to check in | 5 | High | Yes
As a user I want to navigate between screens | 3 | High | Yes
As a user I want to edit my profile | 5 | Low | Yes
As a user I want to create an account | 3 | High | Yes
As a user I want to upload images of possible haircuts | 6 | Medium | Yes
As a user I want to login | 2 | High | Yes
As a user I want to see my stored information | 2 | Medium | Yes
As a user I want to view my visit history and notes | 3 | Medium | Yes
As a shop owner I want to check my upcoming appointments | 2 | High | Yes
As a shop owner I want to check my checkins | 3 | High | Yes
As a shop owner I want to view my contacts | 1 | Medium | Yes
As a shop owner I want to delete a contact from my list | <1 | Medium | No
As a shop owner I want to manage my shop information | 2 | High | No
As a shop owner I want to dismiss completed haircuts | 1 | High | Yes